Annex Four - Steps for Developing an Emergency Plan

1.	Establish your planning process and identify your key sources of information

| Task | Responsibility | Due by | Done | Initial |
| --- | --- | --- | --- | --- |
| Appoint a person to be in charge of the Plan development project and name Plan Coordinator in your Emergency Plan. |  |  |  |  |
| Appoint a Planning Team (between 2-5 people). Name them in your Emergency Plan and include their role in the team. |  |  |  |  |
| Make contact with your local Special Education (Ministry of Education) office. |  |  |  |  |
| Make contact with your CDEM Group office and your local Emergency Management Office (as advised by the CDEM Group). |  |  |  |  |
| Quickly review the emergency material you have available right now and scan the suggested resource. |  |  |  |  |

2.	Identify the specific natural hazards that may affect your ECE service and actions that can be taken to address their consequences

| Task | Responsibility | Due by | Done | Initial |
| --- | --- | --- | --- | --- |
| Identify the hazards and risks that could lead to an emergency for the ECE service. |  |  |  |  |
| Meet with local Emergency Management Office (at the local council) for an update on hazards for the area. |  |  |  |  |
| Complete a hazards list or add to your existing one: - Identify consequences and likelihood - Identify what steps the service could take to reduce any impacts |  |  |  |  |
| List any resulting procedures you have identified you will need. |  |  |  |  |

3.	Involve your community

| Task | Responsibility | Due by | Done | Initial |
| --- | --- | --- | --- | --- |
| Identify which neighbours might be able to help you (and how you might be able to assist them). |  |  |  |  |
| Draw up written arrangements as needed with community partners. |  |  |  |  |

4.	Write your Emergency Plan

| Task | Responsibility | Due by | Done | Initial |
| --- | --- | --- | --- | --- |
| Determine the management structure you will use for emergencies. |  |  |  |  |
| As a team, consider all the things that could generate an emergency and decide on actions to be taken for specific emergency scenarios. |  |  |  |  |
| Appoint staff to be responsible for different roles in an emergency. |  |  |  |  |
| Gather together contact details for staff, contractors, emergency assistance etc. |  |  |  |  |
| Determine how people at the ECE service will know when an emergency has occurred - siren, alarm, flashing lights, phone calls, PA messages, word of mouth, whistles etc. |  |  |  |  |
| Decide how to keep track of visitors on the premises. |  |  |  |  |
| Draw up a locality map showing the ECE service in relation to the wider community. |  |  |  |  |
| Decide on what basis you would close the ECE service. |  |  |  |  |
| Determine your evacuation and shelter-in-place procedures. |  |  |  |  |
| Identify all the safety and emergency resources the ECE service already has and identify what else is needed (for children, staff and pets). |  |  |  |  |
| Ensure you have the necessary information about each of the children in your care and make sure this is an accessible form in an emergency. |  |  |  |  |
| Prepare a list of people with special needs at the ECE service who require extra assistance in an emergency. |  |  |  |  |
| Determine how communication will work with parents during and after emergencies. |  |  |  |  |
| Gather together contact details for staff, contractors, emergency assistance etc. |  |  |  |  |
| Be clear about your ECE service’s child release policies. |  |  |  |  |
| Discuss recovery planning – what will you do to get your ECE service back to normalcy. |  |  |  |  |
| Decide how you will know if your buildings are safe to use after an event. |  |  |  |  |
| Determine what you need to do to be able to reopen the the ECE service and how you will communicate it. |  |  |  |  |
| Determine how to maintain contact and communication with parents if emergency continues or if the ECE service needs to close for a period of time. |  |  |  |  |
| Decide what elements of business continuity you will put in place. |  |  |  |  |
| Make sure you know who to contact for advice on supporting the ongoing emotional health of children and staff. |  |  |  |  |
| Compile important insurance information and have forms ready to record information about damages and losses. |  |  |  |  |
| Ensure you know your ECE services policies around media. |  |  |  |  |
| Determine a structure and layout for your Emergency Plan. |  |  |  |  |
| Fill in the detail of the Emergency Plan. |  |  |  |  |
| Ask your local Emergency Management Office for advice on content. |  |  |  |  |
| Complete any written or graphic material that needs to be displayed in public. |  |  |  |  |
| Make sure everyone in the Planning Team reviews the draft. |  |  |  |  |
| Ensure the Emergency Plan is approved by the ECE service provider. |  |  |  |  |
| Advise parents, staff, and neighbours of the Emergency Plan. |  |  |  |  |

5.	Put your Emergency Plan in place

| Task | Responsibility | Due by | Done | Initial |
| --- | --- | --- | --- | --- |
| Display your evacuation information. |  |  |  |  |
| Erect signs for exits, evacuation routes, assembly areas, shelter-in-place locations, safety equipment and first aid. |  |  |  |  |
| Install emergency warning systems (sirens, PA system) if applicable. |  |  |  |  |
| Develop and deliver a training programme for staff with emergency responsibilities. |  |  |  |  |
| Conduct an exercise based on the Emergency Plan (at least every six months). |  |  |  |  |
| Review the Emergency Plan after every exercise. |  |  |  |  |
| Update contact lists and other information in your Emergency Plan annually (six months is advised). |  |  |  |  |